## Slide 1
Project Kick Off Meeting – Corley Construction
Richland County HMGP/CDBG DR Buyout Program
March 7th, 2019

## Slide 2: Agenda Overview
Staffing
Phases of the Demo process
  Pre-Demolition
  Demolition
  Post-Demolition
  Documentation
GC Questions
Agenda Overview

## Slide 3
  Mike King (Richland County, Local Disaster Recovery Manager)
  Patricia Rock (Richland County, CDBG-DR-Procurement Specialist)
  Donna Overton-Brown (Richland County, Emergency Planner)
  Michela Schildts (Tetra Tech, Program Support)
  Lauren Dozier (Tetra Tech, Program Manager)
  Gregg Culler (Tetra Tech, Field Inspector)
  Mariah GoodwinAmos (Tetra Tech, Program Support)
Program Staffing

## Slide 4: Agenda Overview
Demolition Contractor Verifications & NTP: The County issued an Intent to Award. After the 10-day protest period is over a Notice to Proceed will be issued from the County, and the Contractor can legally enter the site.
Contractor Timeline: From time of executed NTP, the Demolition Contractor will have 45 days to complete asbestos abatement, demolition, and lot restoration.
NTP and Timeline

## Slide 5: Agenda Overview
Demolition and Floodplain Permit: The demolition contractor is responsible for pulling the demolition and floodplain permit through the Richland County Building Department.
  This needs to be done before any work is begun on the property, including asbestos abatement.
  The contractor will need to submit the asbestos report and the contract for the property between the County and the demolition contractor to pull the permit.
    Demolition contractor will have a copy of the asbestos report since it will supplied in the bid package.
Permits

## Slide 6: Agenda Overview
Demolition Inspection Process: Richland County Building Department will complete their own inspections periodically throughout the demo and restoration.
  Richland County will request to review the green space land plan (how the lot needs to be left per the planning department) so they can confirm it is graded properly before they pass the final inspection. This land plan was provided in the bid scope.
Richland County Building Inspections

## Slide 7: Asbestos
Asbestos: If the property has asbestos, it is a DHEC requirement that it be abated per local and federal regulations. The demolition contractor will be responsible for abatement and clearance, including the proper DHEC permits.
Pre-Asbestos Inspection: If asbestos abatement is necessary, Tetra Tech will perform a Pre-Asbestos Inspection before abatement can occur to confirm the property is ready for asbestos abatement and confirm permits have been pulled.

## Slide 8: Utilities
Utility Site Walk-Through: Prior to demolition work commencing at the property, the Demolition Contractor will be required to make-safe utilities to the property. This includes
  Marking easements and underground utilities;
  Removing utility meters; and
  Capping wells, water, sewer, and septic lines to the mains,
  Disconnecting electrical and gas service and propane tanks.

## Slide 9: Pre-Demolition Inspection
Pre-Demolition Inspection: Tetra Tech will perform a Pre-Demolition Inspection to confirm that all utilities have marked and disconnected and the site is ready for demolition.
Demolition Prep: The Demolition Contractor will need to mobilize the appropriate assets to the site for demolition activities and be responsible for providing hauling equipment to transfer the materials to a landfill.

## Slide 10: Unoccupied Inspection
Property Unoccupied Verification: Demolition Contractor re-verifies property description and ownership and notifies Tetra Tech of demolition timeline (date demolition is to start and tentative completion date).
  Before demolition start date, Demolition Contractor verifies structure is unoccupied.
  Tetra Tech will also do a Property Unoccupied Inspection within 24 hours of the scheduled demolition to confirm property vacancy.

## Slide 11: Demolition – Hazardous Materials
Responsibilities:
  Demolition Contractor will remove/dispose of asbestos and other hazardous materials per State of South Carolina environmental and EPA requirements.
  Demolition Contractor will be responsible for disposing of Household Hazardous Waste items per SC DHEC and EPA regulations.
  Demolition Contractor will be responsible for assuming lead-based paint on the property and using lead-based paint safe practices (only for properties built before 1978).
  Demolition Contractor will document items transferred to the landfill.

## Slide 12: Post Demolition
Once demolition is complete, Tetra Tech will complete Post-Demolition Inspection.
In order to pass Post-Demolition Inspection, the following needs to be properly removed from the property:
  Any wooden or metal fencing that belonged to that property
  Mailboxes
  Bricks
  All concrete and materials from the former driveway, up to the County road
  Any general debris such as glass, wood, metal, etc

## Slide 13: Lot Clearing
Once backfilling and final grade is complete, Tetra Tech will complete Post-Lot Clearing and Restoration Inspection.
  Backfill area needs to be clear of all debris prior to backfilling with clean dirt.
  The entire lot needs to be graded properly (ensure the previous driveway area is filled with dirt and graded to the surrounding lot)
  Seeding needs to be complete
Tetra Tech visually re-inspects site within 60 days of completion of backfill for 60 Day Post-Lot Clearing and Restoration Inspection.
  Goal is to ensure that the soils have not sunken, and if required, the Demolition Contractor shall return to stabilize.

## Slide 14: Complete List of Tetra Tech Inspections
Pre-Asbestos Abatement Inspection (if applicable)
Pre-Demolition Inspection
Property Unoccupied Verification Inspection
Post-Demolition Inspection
Post-Lot Clearing and Restoration Inspection
60-Day Post-Lot Clearing and Restoration Inspection

## Slide 15: Program Documentation
The this program requires that all demolition related-files be captured and retained. Tetra Tech maintains all program files which will contain the required documentation.
  This file will contain photo-documentation of the process before, during, and post-demolition.
The demolition contractor will be responsible for submitting the load tickets/landfill manifests to account for debris removed from the property. If any asbestos debris was removed, or HHW items, the demolition contractor will also need to submit the hazardous waste load tickets/landfill manifests.

## Slide 16: Questions?